## By name
Person | Question | Week: <29-04-2020> |  | Week: <06-05-2020> |  | Week: <13-05-2020> |  | Week: <20-05-2020> |  | Week: <27-05-2020>
|  | Monday | Wednesday | Monday | Wednesday | Monday | Wednesday | Monday | Wednesday | Monday | Wednesday
Anshul | What did you do yesterday? |  | Python understanding |  | Issue#3 on GitHub |  | Resolved data migration issue from sqlite to Postgres | Learning Selenium for testing | Issue#16, Debugged Image upload to AWS S3
| What will you work on today? |  | Issue#3 on GitHub |  | Issue#8 on GitHub |  | AWS account creation and learning for AWS S3 | Writing Test cases for Sprint 0 | Issue#19, Issue#21 from GitHub
| Do you have any obstacles? |  | Windows crashed |  | NA |  | NA | Test Framework setup, Chrome WebDriver not working properly | NA
Beer Inder | What did you do yesterday? |  | GitHub Setup, Prepared Landing Page |  | Migrating database from Sqlite to Postgres |  | AWS account creation and learning for AWS S3 | Learning Selenium for testing | Issue#14, Issue#15, Issue#16 from GitHub
| What will you work on today? |  | Issue#4, Issue#5 on GitHub |  | Issue#11 on GitHub |  | Debug Issue#12, User image not displaying after uploading from Admin credentials - Debug Issue#13, App Deploy on Heroku | Writing Test cases for Sprint 0 | Issue#6, Issue#7 from GitHub
| Do you have any obstacles? |  | Using Postgres DB with Django |  | Database not updated properly |  | Image not getting displayed | NA | NA
Tarun | What did you do yesterday? |  | Python understanding, YouTrack Setup |  | Issue#5 on GitHub - HTML Form creation - Reading DB for the User - Loading DB in to the HTML form |  | App Deploy on Heroku |  | Issue#14 from GitHub, Bug
| What will you work on today? |  | Issue#5 on GitHub |  | Issue#5 on GitHub - Getting the data from HTML forms to views - Store the updated data into User Database |  | Debug Issue#13, App Deploy on Heroku |  | Issue#10, Issue#18 from GitHub
| Do you have any obstacles? |  | Pycharm not working |  | NA |  | App not deploying on Heroku and giving errors |  | NA